## PROCEDURE INSTRUCTIONS
Connecticut Department of Administrative Services | 7341 Change Order Proposal Workbook
All Change Order Proposals (COP) prepared by the General Contractor (GC), Construction Manager-at-Risk (CMR) or Subcontractor must be submitted on DAS approved forms. DAS reserves the right to alter the format of this Form 7341 Change Order Proposal Workbook (the "Workbook"), at its option, during the course of the project. All computations will be consistent with the contract specifications and will not amend the contract documents. The Workbook will be made available to each GC/CMR electronically via the Department's website. It is expected that the GC/CMR will distribute the Workbook electronically to each of their first-tier Subcontractors . The Workbook is formatted in Microsoft Excel® for calculations. A Workbook may be completed manually in the event that a user does not have the necessary computer capability. The Workbook is formatted as "Read Only" to ensure that the original calculation formulas are not altered. Use the "Save As" command to save the file under a different file name (e.g., "COP#3"). The user may want to make a master "Read Only" file for each entity to keep unique data (such as name, labor information etc.). Only the blank cells that require input from the user, lightly outlined, will accept data, all other cells are protected. All calculations are done electronically. Enter credit numbers using standard symbols "-" or "( )." GC INSTRUCTIONS: "FORM 7341-GC ONLY" must be completed by the GC as described below; CMR INSTRUCTIONS: "FORM 7341-CMR ONLY" must be completed by the CMR as described below: Change Order & Project Information: Form 7341 must be addressed to the DAS Project Manager and indicate the name of the GC/CMR. Enter the Change Order Proposal Number, Date, DAS Project Number, Project Name and Location and a description of the proposed change. Proposed Material(s) and/or Equipment: The GC/CMR must indicate the Proposed Material(s) and/or Equipment to be used by Quantity, Unit (ft., sq. ft., yd. etc.), Description and Unit Cost. The Cost per item and the Total Charge will be electronically calculated. A number must appear in the Quantity column for each item. Note that Lump Sum costs are not acceptable, except at the sole discretion of the Project Manager, and will require supporting documentation. If necessary, additional line items may be entered on Change Order Proposal Workbook Continuation Page M-E (“Worksheet M-E”). Labor Classification: The GC/CMR must enter the Labor Classification and indicate the Number of Workers, Total Hours (the total hours worked for all workers per line item), Prevailing Labor Rate per Hour, Taxes on Labor, Worker's Compensation and Hourly Benefits. All entries must correspond to the job classification rates in the Prevailing Wage Schedule and as indicated on the Certified Payroll reports. A copy of the latest Certified Payroll report must be attached to verify the labor taxes and benefits. If necessary, additional line items may be entered on Change Order Proposal Workbook Continuation Page LC (“Worksheet LC"). GC/CMR Overhead and Profit: Overhead and Profit is automatically calculated by ranges. This amount will be zero if the Total Material and Labor Charge results in a net Credit. Additional Bond Premium Cost: If conditions warrant, such as pursuant to Article 13 of the General Conditions and/or at determination of the final contract value if the value is increased by change orders, include the cost for additional Bond Premium. Attach an invoice or other verification of the additional bond premium issued by the Surety or its authorized agent. DO NOT INCLUDE ADDITIONAL COSTS FOR INSURANCE. Subcontractors: If applicable, the GC/CMR must list the name of each first-tier Subcontractor associated with this change, the Trade, and the Total Amount charged by each first-tier Subcontractor. Additional first-tier Subcontractors can be listed on Change Order Proposal Workbook Continuation Page AS (“Worksheet AS”). NOTE: Each first-tier Subcontractor must complete the Change Order Proposal Workbook Subcontractor (“Workbook Subcontractor”). The GC/CMR must attach all Change Order Proposal Workbook Subcontractor worksheets with their Form 7341. 6% GC Markup on Subcontractor Cost: The 6% Markup Percentage is automatically calculated. This amount will be zero if the Total Material and Labor Charge results in a net Credit. CMR FEE % Markup on Subcontractor Cost: The CMR must enter their CMR Fee %, as stated on their contract. The Markup Percentage is automatically calculated. This amount will be zero if the Total Material and Labor Charge results in a net Credit. FIRST-TIER SUBCONTRACTOR INSTRUCTIONS: Each first-tier Subcontractor must complete the Change Order Proposal Workbook Subcontractor (“Workbook Subcontractor”) following the instructions provided above. Additional line items can be entered on worksheets M-E and LC. If applicable, the first-tier Subcontractor must provide the Total Secondary Subcontractor’s Costs by listing the Secondary Subcontractors on Change Order Proposal Workbook Continuation Page AS (“Worksheet AS”). Each First-Tier Subcontractor must submit their Workbook to the GC/CMR. 6% Subcontractor’s Markup on Secondary Subcontractors: The 6% Markup is automatically calculated and is limited to the Secondary Subcontractor only (not lower tier subcontractors). This amount will be zero if the Total Material and Labor Charge results in a net Credit. DAS Form 7341 (Rev. 01.03.2025)

## FORM 7341-GC ONLY
Connecticut Department of Administrative Services
7341
Change Order Proposal Workbook
Attached to and made part of Change Order Proposal Number:
To: | Project Manager | [7 empty] | Date:
From: | GC | [7 empty] | Project Number:
Proposed | [6 empty] | Project Name:
Change: | [6 empty] | Project Location:
Quantity | Unit | Proposed Material(s) and/or Equipment | [5 empty] | Unit Cost | Item Cost
0
0
0
0
0
0
0
0
Use Continuation Worksheet M-E for Additional Material(s) and/or Equipment | [8 empty] | 0
[9 empty] | Total Material(s) and/or Equipment Cost | 0
Labor Classification |  |  | No. of Workers | Total Hours | Prevailing Labor Rate | Taxes on Labor | Worker's Compensation | Hourly Cash Benefits | Labor Cost
0
0
0
0
0
Use Continuation Worksheet LC for Additional Labor Classifications | [8 empty] | 0
[9 empty] | Total Labor Cost | 0
[9 empty] | Total Material and Labor Cost | 0
General Contractor's Overhead and Profit |  |  | To $5,000.00 20% |  |  |  | $15,001.00 to $25,000.00 15%
|  |  | $5,001.00 to $15,000.00 17% |  |  |  |  | $25,000.00 and greater 12%
[9 empty] | Total General Contractor's Overhead and Profit | 0
[9 empty] | Total General Contractor's Charge | 0
Additional Bond Premium Cost
Subcontractor(s) -see attached worksheets | [6 empty] | Trade |  | Cost
Use Continuation Worksheet AS for Additional Subcontractors | [8 empty] | 0
[9 empty] | Total Subcontractor(s) Cost | 0
[9 empty] | 6% General Contractor's Markup on Subcontractor Cost | 0
[9 empty] | Total Subcontractor Charge | 0
[9 empty] | Total Proposed Change Order Charge | 0
DAS Form 7341 (Rev. 12.06.2024)

## FORM 7341-CMR ONLY
Connecticut Department of Administrative Services
7341
Change Order Proposal Workbook
FOR CMR FIRMS ONLY
Attached to and made part of Change Order Proposal Number:
To: | Project Manager | [7 empty] | Date:
From: | CMR | [7 empty] | Project Number:
Proposed | [6 empty] | Project Name:
Change: | [6 empty] | Project Location:
Quantity | Unit | Proposed Material(s) and/or Equipment | [5 empty] | Unit Cost | Item Cost
0
0
0
0
0
0
0
0
Use Continuation Worksheet M-E for Additional Material(s) and/or Equipment | [8 empty] | 0
[9 empty] | Total Material(s) and/or Equipment Cost | 0
Labor Classification |  |  | No. of Workers | Total Hours | Prevailing Labor Rate | Taxes on Labor | Worker's Compensation | Hourly Cash Benefits | Labor Cost
0
0
0
0
0
Use Continuation Worksheet LC for Additional Labor Classifications | [8 empty] | 0
[9 empty] | Total Labor Cost | 0
[9 empty] | Total Material and Labor Cost | 0
CMR's Overhead and Profit |  |  | To $5,000.00 20% |  |  |  | $15,001.00 to $25,000.00 15%
|  |  | $5,001.00 to $15,000.00 17% |  |  |  |  | $25,000.00 and greater 12%
[9 empty] | Total CMR's Overhead and Profit | 0
[9 empty] | Total CMR's Charge | 0
ENTER Additional Bond Premium Cost (DO NOT INCLUDE ANY ADDITIONAL INSURANCE COSTS)
Subcontractor(s) -see attached worksheets | [6 empty] | Trade |  | Cost
Use Continuation Worksheet AS for Additional Subcontractors | [8 empty] | 0
[9 empty] | Total Subcontractor(s) Cost | 0
[6 empty] | ENTER CMR Fee Percentage (%) |  |  |  | 0%
[6 empty] | CMR Fee Percentage (%) markup on Subcontractor Cost |  |  |  | 0
|  |  |  | Total Subcontractor Charge (DO NOT INCLUDE ANY ADDITIONAL INSURANCE COSTS) | [5 empty] | 0
|  |  |  | For Deducts/Credit Change Orders: REDUCTION IN CMR FEE (using CMR Fee %): | [5 empty] | 0
[9 empty] | Total Proposed Change Order Charge | 0
DAS Form 7341 (Rev. 01.03.2025) | [9 empty] | 0

## WORKSHEET M-E
7341 Change Order Proposal Workbook Continuation Worksheet Material(s) and/or Equipment (M-E)
[6 empty] | Attached to and made part of Change Order Proposal Number: | 0
To: | Project Manager |  | 0 |  |  | Date: | 0
M
From: | GC/CMR |  | 0 |  |  | Project Number: | 0
Proposed |  | 0 |  | Project Name: | 0
Change: |  |  |  | Project Location: | 0
Quantity | Unit | Additional Proposed Material(s) and/or Equipment |  |  | Unit Cost | Item Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[6 empty] | Total Additional Material(s) and/or Equipment Cost | 0
DAS Form 7341 (Rev. 12.06.2024)

## WORKSHEET LC
7341 Change Order Proposal Workbook Continuation Worksheet Labor Classification (LC)
[9 empty] | Attached to and made part of Change Order Proposal Number: | 0
To: | Project Manager |  | 0 | [5 empty] | Date: | 0
From: | GC/CMR |  | 0 | [5 empty] | Project Number: | 0
Proposed |  | 0 |  |  |  |  | Project Name: | 0
Change: | [6 empty] | Project Location: | 0
Additional Labor Classification |  |  | No. of Workers | Total Hours | Prevailing Labor Rate | Taxes on Labor | Worker's Compensation | Hourly Cash Benefits | Labor Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[9 empty] | Total Additional Labor Cost | 0
DAS Form 7341 (Rev. 12.06.2024)

## WORKSHEET AS
7341 Change Order Proposal Workbook Continuation Worksheet Additional Subcontractors
[6 empty] | Attached to and made a part of Change Order Proposal Number: | 0
To: | Project Manager |  | 0 |  |  | Date: | 0
From: | GC/CMR |  | 0 |  |  | Project Number: | 0
Proposed |  | 0 |  | Project Name: | 0
Change: |  |  |  | Project Location: | 0
Additional Subcontractor(s) -see attached worksheets |  |  |  | Trade |  | Cost
0
DAS Form 7341 (Rev. 12.06.2024)

## WORKBOOK SUBCONTRACTOR
7341 Change Order Proposal Workbook Subcontractor
Department Of Construction Services
[10 empty] | Attached to and made part of Change Order Proposal Number: | 0
| To: | GC/CMR |  | 0 | [5 empty] | Date: | 0
| From: | Subcontractor | [7 empty] | Project Number: | 0
| Proposed |  | 0 |  |  |  |  | Project Name: | 0
| Change: | [6 empty] | Project Location: | 0
| Quantity | Unit | Proposed Material and/or Equipment | [5 empty] | Unit Cost | Item Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
| Use Continuation Worksheet M-E for Additional Material(s) and/or Equipment | [8 empty] | 0
[10 empty] | Total Material(s) and/or Equipment Cost | 0
| Labor Classification |  |  | No. of Workers | Total Hours | Prevailing Labor Rate | Taxes on Labor | Worker's Compensation | Hourly Cash Benefits | Labor Cost
0
0
0
0
0
| Use Continuation Worksheet LC for Additional Labor Classifications | [8 empty] | 0
[10 empty] | Total Labor Cost | 0
[10 empty] | Total Material and Labor Cost | 0
| Subcontractor's Overhead and Profit |  |  | To $5,000.00 20% |  |  |  | $15,001.00 to $25,000.00 15%
|  |  |  | $5,001.00 to $15,000.00 17% |  |  |  |  | $25,000.00 and greater 12%
[10 empty] | Total Subcontractor's Overhead and Profit | 0
[10 empty] | Total Subcontractor's Charge | 0
[10 empty] | Total Secondary Subcontractor's Cost (use Continuation Worksheet AS to list Secondary Subcontractors) | 0
[10 empty] | 6% Subontractor's Markup on Secondary Subcontractor Cost | 0
[10 empty] | Total Proposed Subcontractor's Charge | 0
| ATTEST: | The above-named subcontractor hereby certifies to the best of his/her knowledge and belief that the foregoing Change Order Proposal Workbook is
correct.
By:
(Rev. 12.06.2024) |  |  | typed or printed name |  |  |  | signature |  |  |  | date