NEEDS

- Lack of a national consensus on the scope of the issue for supporting families with a member with IDD across the lifespan.

- Lack of sustainable national and state policies, practices, and systems related to providing supports to families.

- Lack of tools and resources to guide policy, practice and systems transformation to focus and support the role of families.

INPUTS

- Project Management Team providing project coordination and technical assistance– National Association of State Directors of Developmental Disabilities Services (NASDDDS); Univ. of Missouri Institute for Human Development (UMKC-IHD); Human Services Research Institute (HSRI)

- National Partnership Council providing content expertise – NASDDDS; National Assoc. of Councils on Developmental Disabilities; Parent to Parent USA; Self-Advocates Becoming Empowered (SABE); Autistic Self-Advocacy Network; Sibling Leadership Network; Consortium for a National Agenda on Supports to Families

- Significant state and national knowledge base, and policy based experience to draw upon

- $250,000/year for 5 years federal funds

- In-kind State/Local matching funds

ACTIVITIES

1	Develop & Refine Model Framework

1.1	ID innovative and emerging practices for supporting families

1.2	Develop and refine Model Framework

1.3	Develop self-assessment tool

2	Develop/Facilitate Multi-Level CoP

2.1	Develop CoP within 5 States

2.2	Support a State-to-State Peer Consortia (between 5 States above)

2.3	Establish National CoP on Supporting Families

3	Capture/Share Lessons Learned

3.1	Data collection on State and national CoP for replication and knowledge transfer

3.2	Develop and disseminate products and resources

3.3	Support sustainability of multi-level CoP

OUTPUTS

1.1	Promising state practices publication

1.2	Model Framework publication

1.3	State Self-Assessment Tools

2.1	CoP within 5 States

- Applications from 5/more States

- 5 trained facilitators

- 5 state plans

- Annual reports for states

- Sustainability plans for states

2.2	State-to-State Consortia

- 48 virtual meetings

- 5 trained facilitators

- Website, social media, listservs, online reporting tools

2.3	National CoP

- 5 annual face-to-face meetings

- 10 virtual webinars

3.1	Lessons learned report

3.2	Published Guide Book

3.3	Ongoing National CoP

PROJECT GOAL

To build capacity through a Community of Practice across and within States to create policies, practices and systems to better assist and support families than include a member with intellectual and developmental disabilities (IDD) across the lifespan.

OUTCOMES

- State and national consensus on a national framework and agenda for improving support for families with members with IDD.

- Enhanced national and state policies, practices, and sustainable systems that result in improved supports to families.

- Enhanced capacity of states to replicate and sustain exemplary practices to support families and systems.